## Slide 1
Business Process Excellence
SteerCo status updated
June-2020
Tech & Ops
1 June,2020

## Slide 2
Agenda
03
Project Governance
04
BPE Project Progress Dashboard
02
Project Team
05
Tech & Ops Sectors Project Milestones Dashboard
06
01
Project Objectives & Scope
07
What is Next?
Key Achievements Till Date

## Slide 3
Project Background & Objectives
Tech & Ops aims to achieve the following objectives:
Improve and Model Tech & Ops Business processes as per industry best practices
01
Establish a centralized governance and unified repository for business processes
02
Support and contribute to the Tech & Ops operational excellence and digital transformation objectives
04
Achieve better alignment between business process management and automation teams
03
Support the realization of the process and quality oriented culture within Tech & Ops
05

## Slide 4
Process
Automation
Culture
KPIs
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 25 | 25 | 25 | 25
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 25 | 25 | 25 | 25
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 25 | 25 | 25 | 25
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 25 | 25 | 25 | 25
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 25 | 25 | 25 | 25
Chart: 
| Process | KPIs | System | Quality
Excellence | 100 | 100 | 100 | 100
GD | 44 | 40 | 48 | 28
Sector Mean
T&O Mean
2019 OXI Score
42% Established
Chart: 
| Weightage Criteria
Process | 0.4
KPIs | 0.3
Automation | 0.2
Culture | 0.1
Weightage Criteria
0 – 20% | Initial
21 – 40% | Basic
41 – 70% | Established
71 – 90% | Mature
91 – 100% | Excellent
Domain | 2019 % Score (baseline) | 2020 % Score (target)
Process Maturity (Process) | 44 | 80
Measurement & Controlling (KPIs) | 40 | 75
Automations | 48 | 75
Quality Culture | 28 | 75
2020 OXI Score
75% Mature
75
75
75
75
Baseline
Target
Business Process Excellence – Overall Targets
Tech & Ops aims to achieve the following overall targets by December 2020:
 | Baseline 2019 | Target 2020
Tech&Ops | 42% | 75%
Infrastructure | 61% | 80%
CAD | 37% | 70%
CS | 30% | 70%
Application | 40% | 77%
EA | 30% | 70%
Operations | 42% | 75%
TP | 56% | 80%

## Slide 5
Business Process Excellence – Overall Targets
4
3
1
2
2
3
5
1
4
Common Target
to Achieve
Tech & Ops OXI 75%
by Dec 2020
Faster process change and adoption through adequate process governance collaboration capabilities.
Streamlined and consolidated process model across Tech & Ops, thus supporting faster time-to-value for Tech & Ops services.
Improve the skills of the staff to perform their activities reducing errors, promoting SMEs as Quality Champions in their domains.
Enhanced overall automation mechanism through better alignment between Business Process Management and Automation teams.
Improve customer experience for Tech & Ops internal and external customers, contributing to strategic STC objectives.
Process Change Governance
Automation
Training and Knowledge Transfer
Customer Experience
Cross-functional process alignment and harmonization
Sample Benefits of BPE for Tech & Ops Sectors

## Slide 6
Project Team
Program Sponsor
Ayman Qammaz
Khalid Abdelaal
Program Director
Bilal Moussa
Abdulaziz Ghboun
Program Manager
Jose Oliveros
Back Office Support
BPM –
Operations
STC Program Sponsor
Abdullah M. Alowini
Haytham A. Alshehry
STC Program Director
Mohammed A. Alroeis
STC Program Manager
Abdulaziz Almuaiquel
BPM – Infrastructure / EA
BPM –
Apps / Analytics / CyberSecurity
Tools & Reporting
Operational Excellence
Senior BPM Consultant
Track Leader
Senior BPM Consultant
Track Leader
Senior BPM Consultant
Track Leader
BPM Consultants
BPM Consultants
BPM Consultants
Senior Consultant
Track Leader
BPM Tool
(SAG ARIS) Consultant
Analytics Tool (TABLEAU)
Consultant
SMEs
Telecom SME
GDs SMEs
GDs Process Owners
GDs Process Owners
GDs Process Owners
STC Quality Control
Dawi M. Alshalawi
BPM Consultant
BPM Consultant
BPM Consultant
LEGEND
STC Track Leader
Rayan Khuris
STC Track Leader
Abdulaziz AlMuaiqel
STC Track Leader
Shaman Alanazi
Program Change Mgmt.
Pascal Soltysiak
Cross-Integration
Cross-Integration Leader

## Slide 7
Project Governance
Workgroups
Steering Board
VPs / GMs
Project Management Team
Change Request
Change Request
Recommendation
Project Team
Progress
Issues / Risks
Progress
Issues / Risks
Decisions
Approved Changes
Progress
Issues / Risks
Assignments
Deliverables Approval
Decisions
Approved Changes
Change Management Team
Awareness & training
Ownership & Responsibility
Motivation & Recognition
Review Board
SVP / VPs
Change Board
Progress
Issues / Risks
Strategic Alignment
Change Request
Recommendation
Strategic Decisions
Approved Changes
Quarter
Monthly
Weekly
GDs SMEs and process owners are members of the Project Team and the Change Management Team.
VPs to attend first three Steering Board meetings.
Next Steering Board will take place on Jun 21st.

## Slide 8
Project Scope Description
The scope is composed of two parallel tracks:
Operational Excellence Maturity Model Dimensions
Process Governance and & Management
Performance Management
(SLAs, KPIs)
Systems and Tools and Reporting
People Capabilities and Culture
Audit and Control Methods
Data
Operational Excellence Roadmap
……………
Business process governance and management practice
0 1
Business Process Modeling and Improvement
0 2
Business Process Management Tooling(*)
0 3
Business Process Performance Management and Monitoring (Metrics Dashboarding & Reporting)
0 4
Implementation of a holistic business process excellence practice
Business Process Excellence
Technology &
Operations
Business Process Management
…..

## Slide 9
Risks | Severity | Impact | Suggestion/Solution | Management Support
New STC Policy against current Virus situation (accessibility & meeting ) | Moderate |  | Continue leveraging digital communication channels and remote access to required STC resources (e.g., ARIS, process documentation repositories, etc.). | 
Dependency between Operational Excellence Project and other Tech & Ops Project (Lean, Inspiration, DTO, ..etc.) | Moderate |  | On-going identification of relevant initiatives (on-going and planned) to direct other projects heads to keep full alignment and communication between projects especially incase the other project involve developing and updating processes. | 
Frequent Organizational / Structural & mandate changes. | High |  | The project team shall be informed for any prior organizational / structural changes that need to update / modify the technology and operations processes. To involve (or at least consult) the program manager for any potential changes on the technology and operations restructuring activities. | 
Issues | Severity | Impact | Suggestion/Solution | Management Support
Program Benefits
Key Accomplishments
PROGRAM PROGRESS
FINANCIAL PROGRESS
Actual
7%
Planned
7%
RAQAMI-L
Program Information
Project Status
Planned
In Progress
Minor (2% < 5%) Delay
Timeline
Actual
Baseline Plan
Revised Plan
Milestones
Forecast
Completed
Minor Delay
Delayed
Legend
Risks/Issues
Low
Moderate
High
Major (> 5%) Delay
Planned
Program Deliverables
Targets / KPIs - 2020
M
Multi-year program, planned to conclude beyond 2020
Program Beneficiary: Tech & Ops
Program Vendors: Solution, Devoteam
Program Manager: Mohammed A. Alroeis
Accomplish higher level of Tech & Ops maturity and align various projects that include Operation Excellence scopes.
OX Maturity Framework completed. Deliverables submitted for approval.
BPM Framework and Governance deliverables submitted for approval.
On-going analysis of information provided by SMEs from all GDs.
On-going configuration of ARIS (testing environment).
Achieve Efficiency Increase/ Revolutionize culture towards Agility
AE5: Business Process Excellence
RA2: Building New Way of Work with Agile
Accomplish higher level of Tech & Ops maturity and align various projects that include Operation Excellence scopes. 22 Assessment reports.
Departmental Functional Alignment.
Maturity Level and Process improvement and excellence
Sprints timelines might be adjusted to align with process prioritization.
16%
Actual
Planned
16%
Projects | Status | Wtg (%) | Actual / Plan (%) - YTD | Current Milestones | 2020 (70% Target Achievement) |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Business Process Excellence |  | 4% | 100/100 | Initiation & Planning |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 9% | 53/53 | Operational Excellence Roadmap |  |  |  |  |  |  |  |  |  |  |  | 
 |  | 87% | 9/9 | Business Process Management |  |  |  |  |  |  |  |  |  |  |  | 
Envisioning & Preparation
Measurement & Reporting
Analysis &
Roadmap
BP Management Practice Setup
Business Processes Performance
Project Management Plan
Sprint 1
Sprint 2
Sprint 3
Measurement & Reporting
Operational Excellence
Start Date: 09/03/2019
Finish Date: 29/04/2021
2020
Target
70%
2020
Target
60%
62%

## Slide 10
Key Achievements Till Date
Operational Excellence Maturity Framework
Business Process Management Development Framework
Business Process Governance and Compliance Model
Business Process Management
Operational Excellence Roadmap
1
2
3
4
Kick off & Technical meeting
Initiation & Planning

## Slide 11
GDs SMEs Meetings
Sector | Kick-off | Technical Meeting | GD Name | One-to-One #1 | One-to-One #2 | One-to-One #3 | OXM Kick-off | OXM One-to-One
Enterprise Architecture STC – Abdulaziz AlMuaiqel Devoteam – Amer Nasser | 13-Apr-20 | 28-Apr-20 | Technology Strategies and Financials | 3-May-20 | 11-May-20 |  | 15-Jun-20 | 16-Jun-20
 |  |  | Technology and Operations Portfolios | 4-May-20 | 11-May-20 | 20-May-20 |  | 16-Jun-20
 |  |  | Technology Architecture | 30- April-20 3-May-20 12-May-20 | 11-May-20 14-May-20 | 17-May-20 20-May-20 |  | 18-Jun-20
Infrastructure STC – Abdulaziz AlMuaiqel Devoteam – Khalid AlMazroa | 13-Apr-20 | 29-Apr-20 | Cloud Infrastructure | 6-May-20 | 11-May-20 | 20-May-20 | 15-Jun-20 | 18-Jun-20
 |  |  | Infrastructure Planning | 3-May-20 | 12-May-20 | 18-May-20 |  | 17-Jun-20
 |  |  | Infrastructure Design | 4-May-20 | 12-May-20 | 17-May-20 |  | 18-Jun-20
 |  |  | Reports to VP (Inspiration Infrastructure) | 5-May-20 | N/A | N/A |  | 
 |  |  | Infrastructure Implementation | 7-May-20 | 12-May-20 | 17-May-20 16-Jun-20 |  | 
Cyber Security STC – Rayan Khuris Devoteam – Ahmed Salama | 12-Apr-20 | 30-Apr-20 | Cyber Security Governance, Risk and Compliance | 6-May-20 |  |  | 14-Jun-20 | 16-Jun-20
 |  |  | Cyber Defense | 14-May-20 |  |  |  | 
 |  |  | Cyber Security Strategy and Architecture | 7-May-20 | 20-May-20 |  |  | 
Corporate Analytics & Data STC – Rayan Khuris Devoteam – Moath Hamdan | 12-Apr-20 | 28-Apr-20 | Advance Analytics | 12-May-20 | N/A | N/A | 15-Jun-20 | 18-Jun-20
 |  |  | Reports to VP (Analytics Demand Management) | 6-May-20 | N/A | N/A |  | 18-Jun-20
 |  |  | Corporate Analytics Governance | 14-May-20 |  |  |  | 18-Jun-20
 |  |  | Reports to VP (Analytical Strategy and Architecture Program) | 7-May-20 | N/A | N/A |  | N/A
Application STC – Rayan Khuris Devoteam – Ahmed Salama | 12-Apr-20 | 27-Apr-20 | Enterprise Enablement | 11-May-20 |  |  | 14-Jun-20 | 18-Jun-20
 |  |  | Consumer Enablement | 13-May-20 |  |  |  | 17-Jun-20
 |  |  | Organization Enablement | 30-Apr-20 5-May-20 6-May-20 12-May-20 | 14-May-20 | 18-May-20 |  | 
 |  |  | Digital Enablement | 5-May-20 | 18-May-20 |  |  | 17-Jun-20
 |  |  | Application Operations | 7-May-20 |  |  |  | 16-Jun-20
 |  |  | Reports to VP (Projects & Testing) | 4-May-20 |  |  |  | 
 |  |  | Reports to VP (Business & Financial Planning) | 20-May-20 |  |  |  | 
Operations STC – Shaman Alanazi Devoteam – TBC | 12-Apr-20 | 30-Apr-20 | Network Operations | 7-May-20 |  |  | 15-Jun-20 | 
 |  |  | Operations Control | 21-May-20 |  |  |  | 
 |  |  | Customer Service Design & Delivery | 17-May-20 |  |  |  | 
 |  |  | Customer Service Operations | 17-May-20 |  |  |  | 
 |  |  | Technical Facility Management | 18-May-20 |  |  |  | 
Technology Performance STC – Shaman Alanazi Devoteam – TBC | 12-Apr-20 | 29-Apr-20 | Technology Performance | 14-May-20 | N/A | N/A | 15-Jun-20 | 

## Slide 12
2. Operational Excellence Maturity Model
Reference Frameworks and Industry Best Practices
Ongoing consideration for target certifications

## Slide 13
3. Business Process Management Framework
Process Definition, Analysis & Design Principles
BPM Guidelines, Tools and Techniques

## Slide 14
4. Business Process Governance – Model
(*) Tableau has been initially identified as process performance reporting platform, but a final decision will be made by STC.
(*) Integration of ARIS and iGATE is currently under discussion with relevant stakeholders.

## Slide 15
4. Business Process Governance – Framework

## Slide 16
Sectors Project Milestones Dashboard
Infrastructure
Enterprise Architecture
Cyber Security
Corporate Analytics & Data
Technology Performance
In Progress
<+2%
Minor Delay
>2% <=5%
Major Delay
> 5%
Infr. Planning
Infr. Design
Infr. Implementation
Cloud Infrastructure
Tech. & Ops. Portfolio
Tech. Strategies & Fin.
Tech. Architecture
Cyber Defence
Gov., Risk & Compliance
Strategy & Architecture
Advanced Analytics
Analytics Governance
Application
Consumer Enablement
Enterprise Enablement
Digital Enablement
Application Operations
Org. Enablement
Projects & Testing
Bus & Financial Planning
Demand Management
Strategy and Architecture
Operations
Network Operations
Operations Control
Cus. Ser. Design & Deliv.
Cus. Ser. Operations
Tech. Facilities Mgmt.
Planned
11%
Actual
11%
Planned
11%
Actual
11%
Planned
11%
Actual
10%
Planned
11%
Actual
10%
Planned
11%
Actual
11%
Planned
11%
Actual
11%
Planned
11%
Actual
11%

## Slide 17
Next Steps & Required Support
Next Steps
Finalize information gathering from all Sectors.
GDs Information analysis and Sprints design (aligned with SMEs).
ARIS configuration (support from IT and CQM).
OXI measurement.
Sprints execution begins by 1st of July.
Required Support
Finalize the GD’s Mandates and update HR with final R&R to avoid changes and utilize the exercise efficiently as it will be built in ARIS and fixed.
Empower the SMEs with the Authority to:
  Represent the GM and continue to be delegated by him for any demand or approvals needed.
  Complete each GD’s project milestone within the specified timeline
  Share project information with the project team
  Actively participate in process design sprints (process design, reviews, comments, approvals).
Promote and support the Change Management activities, actively promoting the attendance/participation of staff in all change management activities along the program execution.
Reflecting any changes ongoing or planned related to the processes and consider it as part of the information that should be shared and reviewed mutually.

## Slide 18
Thank you